## Sheet1
S NO | EPIC_ID | EPIC | USER STORY_ID | USER STORY | ACCEPTANCE CRITERIA | TEST SCENERIO ID | TEST CASE ID | STATUS | DEFECT ID
1 | EP_001 | REGISTER ON CBI APPLICATION | US_001 | As a new user,I want to register for the Central Banking application by providing my personal details(name,email,phone number) so that I can create an account and start accessing banking services | Given the new user is on the Central Banking application registration page when the user provide their personal details(name, email, phone number) and click register then the account should be created successfully | TS_CBI_001 | TC_CBI_001 | PASS
[7 empty] | TC_CBI_002 | FAIL | CBI_002
[7 empty] | TC_CBI_003 | PASS
|  |  | US_002 | As a new user, I want to upload my identity documents like ID proof,address etc., so that my identity will be verified for banking services. | Given the new user with a registered account is on the KYC page of the Central Banking application, When Ithe user upload their identity documents (e.g.aadhar no,voted id etc)in pdf format Then the system should verify the uploaded documents and activate the account. |  | TC_CBI_004 | PASS
[7 empty] | TC_CBI_005 | FAIL | CBI_005
[7 empty] | TC_CBI_006 | PASS
2 | EP_002 | LOGIN ON CBI APPLICATION | US_003 | As a user, I want to log in using my email/phone number and password so that I can securely access my Central Banking account | Given the user is on the login page When they enter valid login details and submit it Then they should be authenticated successfully and it should be redirected to their Central Banking account dashboard. | TS_CBI_002 | TC_CBI_007 | PASS
[7 empty] | TC_CBI_008 | PASS
[7 empty] | TC_CBI_009 | FAIL | CBI_009
|  |  | US_004 | As a user, I want to reset my password by verifying my identity through an OTP sent to my registered email or phone number so that I can securely regain access to my account if I forget my current password. | Given the user is on the login page and select forgot password when they enter their registered email or phone number then the system sends an OTP to the provided email or phone number then the user should be prompted to enter it on the verification page. |  | TC_CBI_010 | FAIL | CBI_010
[7 empty] | TC_CBI_011 | PASS
[7 empty] | TC_CBI_012 | PASS
3 | EP_003 | FUNDS TRANSFER | US_005 | As a user, I want to transfer money between my own accounts (e.g., from savings to checking) so that I can manage my money easily. | Given the user on the "Transfer Funds" page of the Central Banking application When they select the source account (e.g., savings) and destination account (e.g., checking) and confirm the transfer then the money should be transferred succesfully. | TS_CBI_003 | TC_CBI_013 | PASS
[7 empty] | TC_CBI_014 | PASS
[7 empty] | TC_CBI_015 | PASS
|  |  | US_006 | As a user, I want to send money to an external bank account so that I can transfer money to others. | Given the user is on the "Send Money" page of the Central Banking application when they entered the recipient's external bank account details and confirm the transfer by clicking the "Send" button then the transfer sholud be authenticated and done successfully |  | TC_CBI_016 | FAIL | CBI_016
[7 empty] | TC_CBI_017 | PASS
[7 empty] | TC_CBI_018 | FAIL | CBI_018
4 | EP_004 | CUSTOMER SERVICE REQUEST | US_007 | As a user, I want to request a new ATM/Credit/Debit card through the customer service section of the app so that I can receive a new card if my card is lost, damaged. | Given the user is on the on the customer service section of the Central Banking application,when they select the option to request a new ATM/Credit/Debit card and indicated the reason(lost or damaged) then the request for a new card should be successfully processed. | TS_CBI_004 | TC_CBI_019 | FAIL | CBI_019
[7 empty] | TC_CBI_020 | FAIL | CBI_020
[7 empty] | TC_CBI_021 | PASS
|  |  | US_008 | As a user, I want to report my ATM/credit/debit card lost or stolen through the app so that the bank can block my card and prevent unauthorized transactions. | Given the user is on the on the customer service section of the Central Banking application when the user reports ATM/credit/debit card lost/stolen then the bank should block their card and prevent any unauthorized transactions. |  | TC_CBI_022 | PASS
[7 empty] | TC_CBI_023 | PASS
[7 empty] | TC_CBI_024 | PASS
5 | EP_005 | LOAN | US_009 | As a user, I want to apply for a loan (personal, home, education, etc) through the Central Banking Application so that I can request financial help for various needs. | Given the user is on the loan application section of the Central Banking application When they select the type of loan they want to apply for Then they should receive a confirmation message acknowledging the submission | TS_CBI_005 | TC_CBI_025 | FAIL | CBI_025
[7 empty] | TC_CBI_026 | PASS
|  |  | US_010 | As a user, I want to check my eligibility for a loan (based on my credit score) so that I can understand whether I qualify before submitting a formal application. | Given the user is on the loan application section of the Central Banking application when they enter their personal and financial details Then the system should calculate the user's loan eligibility based on the provided information and the user's credit score.
[7 empty] | TC_CBI_027 | PASS
[7 empty] | TC_CBI_028 | FAIL | CBI_028
|  |  | US_011 | As a user, I want to track the status of my loan application so that I can know when my loan request will be approved or rejected and get updates or next steps. | Given the user is on the loan application section of the Central Banking application sectionwhen they select the option to track their loan application status Then they should be able to see the current status of their loan application (e.g., approved, rejected) |  | TC_CBI_029 | PASS
[7 empty] | TC_CBI_030 | PASS |  | 2
6 | EP_006 | MANAGE OR SCHEDULE BILL | US_012 | As a user, I want to schedule recurring bill payments (e.g., utilities, subscriptions) that I don’t have to manually make payments every month. | Given the user is on the bill payments section of the Central Banking application When they select the option to schedule a recurring payment Then they should be able to choose the type of bill (e.g., utilities, subscriptions) | TS_CBI_006 | TC_CBI_031 | PASS
[7 empty] | TC_CBI_032 | PASS
[7 empty] | TC_CBI_033 | PASS
|  |  | US_013 | As a user, I want to view and manag my upcoming scheduled bills so that I can ensure payments are made on time and adjust any details if necessary. | Given the user is on the bill payments section of the Central Banking application When they view the list of upcoming scheduled bills Then they should be able to modify information such as bill type, amount, due date, and payment frequency. |  | TC_CBI_034 | PASS
[7 empty] | TC_CBI_035 | PASS
[7 empty] | TC_CBI_036 | PASS